## Schedule TeamF
No. | Tasks |  | Assignment | Progress | Status | May | [13 empty] | June
[6 empty] | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
0 | Portfolio preparation |  | All | 100% | bar: May 18 to May 20
| 0.1 | Reading Portfolio requirements | All | 100%
| 0.2 | Tasks breakdown | Yun | 100%
| 0.3 | Team Agreements | All | 100% | bar: May 20
1 | About the Organization(Foodstuffs) 10% |  | All | 0% | bar: May 20 to May 21
| 1.1 | First version(Vision, Mission, Goals, Objectives) | Melvina | 0% | bar: May 20 to May 22
| 1.2 | First version(Values, Key Business, Organization Structure, Summary) | Yun | 0% | bar: May 20 to May 22
| 1.3 | Team Agreements | All | 0% | bar: May 22
2 | ICT infrastructure 10% |  | All | 0% | bar: May 20 to May 22
| 2.1 | First version(Introduction, Hardware) | Sergei | 0% | bar: May 20 to May 22
| 2.2 | First version(Software, Current ICT structure, Summary) | Melvina | 0% | bar: May 20 to May 22
| 2.3 | Team Agreements | All | 0% | bar: May 22
3 | Analyse the strategic importance of ICT 30% |  | All | 0% | bar: May 22 to May 27
| 3.1 | Introduction | Sergei | 0% | bar: May 22
| 3.2 | ICT SWOT analysis | Yun | 0% | bar: May 22 to May 26
| 3.3 | ICT PEST analysis | Sergei | 0% | bar: May 22 to May 26
| 3.4 | ICT Balance Scorecard analysis | Qixiang | 0% | bar: May 20 to May 26
| 3.5 | Gartner Quadrant analysis | Tanapol | 0% | bar: May 20 to May 26
| 3.6 | Enterprise Architecture | Melvina | 0% | bar: May 22 to May 27
| 3.7 | Summary | Yun | 0% | bar: May 22 to May 27
4 | Strategic objectives and action plan 30% |  | All | 0% | bar: May 25 to May 30
| 4.1 | introduction | Melvina | 0%
| 4.2 | Based on 4,1 | Yun | 0% | bar: May 26 to May 28
| 4.3 | Based on 4.2 | Sergei | 0% | bar: May 26 to May 28
| 4.4 | Based on 4.3 | Qixiang | 0% | bar: May 25 to May 28
| 4.5 | Based on 4.4 | Tanapol | 0% | bar: May 25 to May 28
| 4.6 | Based on 4.5 | Melvina | 0% | bar: May 26 to May 29
| 4.7 | Summary - Strategic Detail (Objectives, Goals, Action Plans) | Tanapol | 0% | bar: May 29 to May 30
5 | Recommendation of ICT structure 5% |  | All | 0% | bar: May 28 to May 29
| 5.1 | Introduction | Melvina | 0% | bar: May 28 to May 29
| 5.2 | Discuss and Conclusion- Proposed ICT Organisational Structure | Qixiang+All | 0% | bar: May 29
6 | Executive summary 10% |  | Qixiang | 0% | bar: May 29 to May 30
7 | General description of the tasks |  | Yun | 0% | bar: May 29
8 | Preparation for PartA presentation |  | All | 0% | bar: May 30 to May 31
| 8.1 | Draft including portfolio and PPT | Yun | 0%
| 8.2 | Final version | All | 0% | bar: June 1 to June 4
9 | PartA presentation 5% |  | All | 0% | bar: June 5
10 | PartA submission |  | Yun | 0% | bar: June 7
| 10.1 | Modification if any | Yun | 0% | bar: June 7
11 | Improvement of Part A 5% |  | Tanapol | 0% | bar: June 6 to June 7
12 | Improvement of executive summary 5% |  | Qixiang | 0% | bar: June 6 to June 7
13 | Roles of key ICT managers 10% |  | All | 0% | bar: June 6 to June 9
| 13.1 | First version | Sergei | 0% | bar: June 6 to June 7
| 13.2 | Team Agreements | All | 0%
14 | Prepare the policy and planning documents except 14.1 40% |  | All | 0% | bar: June 10 to June 14
| 14.1 | Application of an ICT policy template 5% | Yun | 0% | bar: June 10
| 14.2 | Access Management | Qixiang | 0% | bar: June 10
| 14.3 | Security Management | Tanapol | 0% | bar: June 10
| 14.4 | Social Media | Tanapol | 0% | bar: June 11
| 14.5 | BYOD and Private Usage of Company Devices | Sergei | 0% | bar: June 10
| 14.6 | Communication | Melvina | 0% | bar: June 11
| 14.7 | Privacy and Ethical | Tanapol | 0% | bar: June 11
| 14.8 | Data Management | Sergei | 0% | bar: June 11 to June 12
| 14.9 | Knowledge Management | Melvina | 0% | bar: June 11 to June 12
| 14.10 | Hardware and Software Acquisition, Update and Maintenance | Qixiang | 0% | bar: June 12
| 14.11 | ICT Project Management | Tanapol | 0% | bar: June 12 to June 14
15 | ICT Risk management plan 10% |  | Qixiang | 0% | bar: June 13 to June 16
16 | General description of the tasks |  | Yun | 0% | bar: June 17
17 | Preparation for PartA presentation |  | All | 0% | bar: June 17 to June 23
| 17.1 | Draft including portfolio and PPT | Sergei | 0% | bar: June 17 to June 18
| 17.2 | Final version | All | 0% | bar: June 19 to June 23
18 | PartB presentation 10% |  | All | 0% | bar: June 26
19 | PartB submission |  | Yun | 0% | bar: June 28
| 19.1 | Modification if any | Yun | 0% | bar: June 28